## Foglio1
Ezshop
tasks | start date | hours | people | total | complate date | Adjusted lenght
requirment and deisgn | 2025-10-27 | 35 | 1 | 35 | 2025-10-29 | 2
Requirement analysis and definition | 2025-10-27 | 15 | 5 | 3 | 2025-10-28 | 1
System, architecture and database desing | 2025-10-28 | 20 | 5 | 4 | 2025-10-29 | 1
development | 2025-10-30 | 175 | 1 | 175 | 2025-11-07 | 8
Cash register comunication and API Development | 2025-10-30 | 25 | 2 | 13 | 2025-11-03 | 4
Backend Development | 2025-10-30 | 70 | 2 | 35 | 2025-11-07 | 8
Database and query Development | 2025-11-04 | 50 | 2 | 25 | 2025-11-07 | 3
Frontend Development | 2025-10-30 | 30 | 1 | 30 | 2025-11-04 | 5
Testing | 2025-11-05 | 100 | 1 | 100 | 2025-11-11 | 6
creation | 2025-11-05 | 25 | 1 | 25 | 2025-11-07 | 2
Test | 2025-11-10 | 75 | 5 | 15 | 2025-11-11 | 1
final stage | 2025-11-12 | 40 | 1 | 40 | 2025-11-14 | 2
Create a Documentation | 2025-11-12 | 15 | 2 | 8 | 2025-11-14 | 2
Sundry Feedback | 2025-11-12 | 25 | 3 | 9 | 2025-11-14 | 2